## FE Tasks
Sr No | Module | Task Description | Start Date | Type | Est Time(Hr) | Actual Time | Status | Comment If any
1 | Foundation | Project setup: scaffold, router, folder structure, lint, env config |  | Setup | 2 |  | Not Started | FE-001
2 | Foundation | API client: fetch/axios wrapper, JWT header injection, global 401 handler |  | Setup | 2 |  | Not Started | FE-002 · after FE-001
3 | Foundation | Shared UI kit: Button, Input, Modal, Toast, Error Banner, Loader |  | UI | 4 |  | Not Started | FE-003 · after FE-001
4 | Foundation | Auth store: state management + localStorage sync (crm_token, crm_user) |  | Logic | 2 |  | Not Started | FE-004 · after FE-001
5 | Authentication | Login page UI: logo, layout, responsive, password visibility toggle |  | UI | 3 |  | Not Started | FE-101 · after FE-003
6 | Authentication | Client-side validation: required fields, email format, max 255, trim |  | Validation | 1.5 |  | Not Started | FE-102 · after FE-101
7 | Authentication | Login API integration: loading state, error banner, error clears on typing |  | Integration | 2 |  | Not Started | FE-103 · after FE-002, FE-102
8 | Authentication | Role-based redirect after login (5 role dashboards) |  | Logic | 1.5 |  | Not Started | FE-104 · after FE-103
9 | Authentication | Auth route guard: unauthenticated users redirected to /login |  | Logic | 2 |  | Not Started | FE-105 · after FE-004
10 | Authentication | RBAC route guard: cross-role dashboard access redirected to own dashboard |  | Logic | 2 |  | Not Started | FE-106 · after FE-105
11 | Authentication | Session restore on refresh / new tab (bootstrap + GET /auth/me) |  | Logic | 2 |  | Not Started | FE-107 · after FE-004
12 | Authentication | Token expiry handling: any 401 clears session, redirect to /login |  | Logic | 1.5 |  | Not Started | FE-108 · after FE-002
13 | Authentication | Logout: clear storage, reset state, redirect to /login |  | Logic | 1 |  | Not Started | FE-109 · after FE-004
14 | Authentication | Edge cases: double-click submit, browser offline, corrupted localStorage |  | Edge Cases | 2 |  | Not Started | FE-110 · after FE-103
15 | Authentication | QA checklist pass + bug fixes (auth module) |  | QA | 2 |  | Not Started | FE-111 · after all auth tasks
16 | Lead Creation | Global Add Lead button in header + entry points on dashboard and lead list |  | UI | 1.5 |  | Not Started | FE-201 · after FE-003
17 | Lead Creation | Add Lead modal UI: form fields, layout, close/cancel without saving |  | UI | 3 |  | Not Started | FE-202 · after FE-003
18 | Lead Creation | Country selector + phone input with country-based length validation |  | Validation | 3 |  | Not Started | FE-203 · after FE-202
19 | Lead Creation | Phone-OR-email mandatory rule + email format validation |  | Validation | 1.5 |  | Not Started | FE-204 · after FE-202
20 | Lead Creation | Create Lead API integration: submit, loading state, prevent duplicate submit |  | Integration | 2 |  | Not Started | FE-205 · after FE-002, FE-204
21 | Lead Creation | Success flow: toast, close modal, reset form |  | UI | 1 |  | Not Started | FE-206 · after FE-205
22 | Lead Creation | Realtime subscription: new lead appears in list instantly, reconnect handling |  | Integration | 3 |  | Not Started | FE-207 · after FE-205
23 | Lead Creation | Error handling: 400/403/500, network timeout, user-friendly messages |  | Edge Cases | 1.5 |  | Not Started | FE-208 · after FE-205
24 | Lead Creation | Edge cases + QA checklist pass (lead creation) |  | QA | 2 |  | Not Started | FE-209 · after all lead tasks
Total (buffer excluded — add ~15% when committing dates)
Fill in: Start Date (when you pick up the task), Actual Time (hours spent), Status (dropdown: Not Started / In Progress / Blocked / In Review / Done). Est Time source: user-provided estimates, halved per manager instruction (Jul 2026). FE-xxx codes in Comment map to the task IDs in crm-frontend-tasks.md.